## Budget - Year 1 to 5
IPG |  | Actions | Possible Days | Budget ($) | Total ($)
1 | Bigeye harvest strategy | Lobby WCPFC via flag states to request that the timetable for bigeye in the WCPFC harvest strategy workplan (2017) is respected | 7 | 1400 | 2400
|  | Work with other MSC and FIP fisheries and NGOs for more effective lobbying by the industry in support of harvest strategies for WCPO stocks | 5 | 1000
2 | Skipjack harvest strategy | Lobby WCPFC via flag states to request that the timetable for skipjack in the WCPFC harvest strategy workplan (2017) is respected | 7 | 1400 | 2400
|  | Work with other MSC and FIP fisheries and NGOs for more effective lobbying by the industry in support of harvest strategies for WCPO stocks | 5 | 1000
3 | Yellowfin harvest strategy | Lobby WCPFC via flag states to request that the timetable for yellowfin in the WCPFC harvest strategy workplan (2017) is respected | 7 | 1400 | 2400
|  | Work with other MSC and FIP fisheries and NGOs for more effective lobbying by the industry in support of harvest strategies for WCPO stocks | 5 | 1000
4 | ETP species strategy | Compile full list of ETP species interacting with the gear | 5 | 1000 | 24000
|  | Evaluate gaps in management strategy | 5 | 1000
|  | Improve management strategies where necessary to fill gaps | 30 | 6000
|  | Implement improved management strategies | 50 | 10000
|  | Monitor ETP species interactions and success of management strategies | 30 | 6000
5 | Entangling FADs | Formal commitment to use only non-entangling FADs | 10 | 2000 | 25000
|  | Identify suitable alternative FAD designs | 20 | 4000
|  | Test non-entangling FADs | 50 | 10000
|  | Convert to deploying non-entangling FADs | 30 | 6000
|  | Retrieve non-entangling FADs found during fishing | 15 | 3000
6 | Ecosystem impact of FADs | Agree research plan with scientific institute | 5 | 1000 | 25000
|  | Provide data for research | 20 | 4000
|  | Analyse data and publish research | 50 | 10000
|  | Evaluate management implications | 50 | 10000
7 | Management of FADs | Align use of FADs with WCPFC requirements | 10 | 2000 | 10000
|  | Review management implications of FAD ecosystem research | 10 | 2000
|  | Put in place management to mitigate ecosystem impacts of FADs, if necessary | 30 | 6000
|  |  | 456 | 91200